## Sheet1
GarbageGo
Activity | Start | Changes | Status | Target Date | Assigned Push
Project Start | 6/20/2023
Creating Account in Github | 6/20/2023 | Create Acc | Completed | 6/20/2023 | Alvarez, Bascuguin, Urge
Creating Repository | 6/20/2023 | Add Member/Add Folder | Completed | 6/20/2023 | Bascuguin
Website UI/UX Design | 6/16/2023 | Admin, Staff, Driver Interface | Ongoing | 6/21/2023 | Bascuguin, Urge
Mobile App UI/UX Design | 6/20/2023 | Home Page Interface | Ongoing | 6/21/2023 | Alvarez
Documents | 6/20/2023 | Creating Project Timeline | To Follow | To Follow | Alvarez
Add Minutes Form | 6/21/2023 | Add the Resident in our user | Completed | 6/21/2023 | Alvarez, Bascuguin, Urge